## Summary
PROJECT DELAY COST ESTIMATE WORKSHEET
Instructions: | Please fill out the information for the boxes highlighted in light yellow. The gray boxes will populate automatically but can be manually overridden if needed. Please add additional comments as necessary. The total delay impact will be highlighted in bright yellow.
PROJECT BACKGROUND |  |  |  | ESTIMATED DELAY |  |  |  |  | Monthly
Project Name: |  |  |  | Delay Start Date |  | 2020-03-15 |  |  | Weekly
Project Number: |  |  |  | Delay End Date |  | 2020-04-15 |  |  | Daily
Project Owner: |  |  |  | Total Length of Delay (Days) |  | 31
Project Address
Current Scheduled Date of Completion: |  |  |  | TOTAL ESTIMATED DELAY IMPACT |  | 0
ESTIMATED DELAY COSTS
Description | Monthly / Weekly / Daily (Choose One) | Cost Amount | Estimated Daily Cost | Estimated Delay Cost | Plus: Demobilization / Remobilization Costs | Plus: Other Costs (If Applicable) | Total Impact | Comments
Labor | Daily | 0 | 0 | 0 |  |  | 0 | Linked to "Labor Details Tab" by default
Equipment | Daily | 0 | 0 | 0 |  |  | 0 | Linked to "Equipment Details Tab" by default
General Conditions | Daily | 0 | 0 | 0 |  |  | 0 | Linked to "GC Details Tab" by default
Subcontractors | [6 empty] | 0
Subcontractor 1 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 2 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 3 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 4 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 5 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 6 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 7 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 8 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 9 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 10 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 11 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 12 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 13 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 14 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 15 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 16 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 17 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 18 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 19 | Monthly |  | 0 | 0 |  |  | 0
Subcontractor 20 | Monthly |  | 0 | 0 |  |  | 0
Total Subcontractor |  |  | 0 | 0 | 0 | 0 | 0
Liquidated Damages (If applicable) | Daily |  | 0 | 0 |  |  | 0
GRAND TOTAL |  |  | 0 | 0 | 0 | 0 | 0

## Labor Details
LABOR DETAIL WORKSHEET (OPTIONAL)
Labor Category | Description (Optional) | Monthly Cost | Weekly Cost | Daily Cost | Comments
Project Executives
Project Managers
Superintendents
Project Engineers
Schedulers
Estimators
QA/QC
Safety
Finance / Accounting
Administrative
Miscellaneous Staff
Total |  | 0 | 0 | 0

## Equipment Details
EQUIPMENT DETAIL WORKSHEET (OPTIONAL)
Labor Category | Description (Optional) | Monthly Cost | Weekly Cost | Daily Cost | Comments
Equipment 1
Equipment 2
Equipment 3
Equipment 4
Equipment 5
Equipment 6
Equipment 7
Equipment 8
Equipment 9
Equipment 10
Equipment 11
Equipment 12
Equipment 13
Equipment 14
Equipment 15
Equipment 16
Equipment 17
Equipment 18
Equipment 19
Equipment 20
Total |  | 0 | 0 | 0

## GC Details
GENERAL CONDITIONS DETAIL WORKSHEET (OPTIONAL)
Labor Category | Description (Optional) | Monthly Cost | Weekly Cost | Daily Cost | Comments
Temporary Office
Security
Fencing
Electric
Internet & Phone
Computers & Printers
Waste Removal
Toilets
General Conditions 1
General Conditions 2
General Conditions 3
General Conditions 4
General Conditions 5
General Conditions 6
General Conditions 7
General Conditions 8
General Conditions 9
General Conditions 10
General Conditions 11
General Conditions 12
Total |  | 0 | 0 | 0